## Sheet1
Gantt Chart
Tasks | Start Date | Days Needed
Project Idea Discussion | 2023-11-19 | 4
Study of Similar Systems | 2023-11-22 | 14
Requirement Gathering & Setup | 2023-12-07 | 10
Data Collection | 2023-12-23 | 21
Data Processing & Cleaning | 2024-01-20 | 30
Feature Extraction & Selection | 2024-02-20 | 25
Algorithm Implementation | 2024-03-20 | 20
Model Training Evaluation | 2024-04-10 | 30
Testing & Debugging | 2024-05-10 | 20
Performance Metrices Calculation | 2024-06-01 | 7
Extension UI Development | 2024-06-08 | 15
Documentation | 2024-06-23 | 7