## Sheet1
Gantt Chart
Tasks | Start Date | Days Needed
Project Idea Discussion | 2023-11-19 | 4
Study of Similar Systems | 2023-11-22 | 14
Requirement Gathering & Setup | 2023-12-07 | 10
AR Literature Review | 2023-12-10 | 30
AR Feature Development | 2023-12-23 | 60
Backend Development | 2024-01-20 | 30
Frontend Development | 2024-02-20 | 25
AR Feature Testing & Debugging | 2024-03-20 | 20
Frontend Enhancement | 2024-04-10 | 30
Testing & Debugging | 2024-05-10 | 20
Documentation and Writing | 2024-06-01 | 7
Final Reviews and Submission | 2024-06-08 | 15
Overall Enhancement | 2024-06-23 | 7